## Sheet1
"No Surprises" Management Update
| Project: | The Show Me Challenge - Cycle 2
| Project Owner: | Francesca Haass
| Today's Date: | 2019-08-13
Items for management attention
| Project Variables | Current Status | Notes
| Scope | On track | N/A
| Quality | Off track - plan to resolve | Risk around pitch quality - a couple of pitches will need meaningful coaching to get to the competitive bar. Plan to resolve in place (providing agreed upon feedback, mentorship).
| Effort | On track | N/A
| Risk | On track | N/A
| Timelines | Off track - plan to resolve | We are a couple of days behind on notifying teams on finalist pitches. Plan to resolve - Update to be sent out by Friday 5/10
Goals for next week
| Action |  |  | Date
1 | Notify finalist teams and provide agreed-upon improvement feedback |  |  | 2019-05-10
2 | Notify non-finalist teams and provide overall imrpovement feedback |  |  | 2019-05-10
3 | Connect finalist teams with their coach |  |  | 2019-05-15
Accomplishments from this week
| Action |  |  | Date
1 | Meet with judges to agree on finalist teams |  |  | 2019-05-02
2 | Send out pitches for final judge review and sign-off |  |  | 2019-05-06
3 | Collect feedback from judges for finalist pitch improvements |  |  | 2019-05-08
4 | Select coaches for finalist teams |  |  | 2019-05-09